## Sheet1
[6 empty] | 2 | 2 | 4
SG2-13
[6 empty] | 2 | 0 | 4
[10 empty] | 4 | 2 | 6
SG2-6
[10 empty] | 6 | 2 | 8
[10 empty] | 4 | 2 | 6
SG2-8
[10 empty] | 6 | 2 | 8
0 | 0 | 0 |  |  |  | 2 | 2 | 4 |  | 4 | 2 | 6 | 6 | 2 | 8
START | [5 empty] | SG2-4 |  |  |  | SG2-18 |  |  | SG2-15
0 | 0 | 0 |  |  |  | 2 | 0 | 4 |  | 4 | 0 | 6 | 6 | 0 | 8
[10 empty] | 4 | 2 | 6
SG2-19
[10 empty] | 6 | 2 | 8
[10 empty] | 4 | 3.16 | 7.16
SG2-9
[10 empty] | 4.84 | 0.84 | 8
|  | 0 | 2 | 2 | [5 empty] | 4 | 3.16 | 7.16
|  | SG2-2 | [7 empty] | SG2-11
|  | 0 | 0 | 2 | [5 empty] | 4.84 | 0.84 | 8
[10 empty] | 4 | 2 | 6
SG2-14
[10 empty] | 6 | 2 | 8
[10 empty] | 4 | 3.16 | 7.16 |  |  |  | 8 | 0 | 8
[10 empty] | SG2-17 | [5 empty] | END
[10 empty] | 4.84 | 0.84 | 8 |  |  |  | 8 | 0 | 8
[10 empty] | 4 | 3.16 | 7.16
SG2-10
[10 empty] | 4.84 | 0.84 | 8
[10 empty] | 4 | 2 | 6
SG2-12
[10 empty] | 6 | 2 | 8
[10 empty] | 4 | 2 | 6
SG2-21
[10 empty] | 6 | 2 | 8
[10 empty] | 4 | 2 | 6
SG2-3
[10 empty] | 6 | 2 | 8
[10 empty] | 4 | 2 | 4
SG2-7
[10 empty] | 6 | 2 | 8
[10 empty] | 4 | 3.16 | 7.16
SG2-22
[10 empty] | 4.84 | 0.84 | 8
[6 empty] | 2 | 2 | 4 |  | 4 | 3.16 | 7.16
[6 empty] | SG2-5 |  |  |  | SG2-16
[6 empty] | 2 | 0 | 4 |  | 4.84 | 0.84 | 8
[10 empty] | 4 | 2 | 6
SG2-20
[10 empty] | 6 | 2 | 8
[10 empty] | 4 | 3.16 | 7.16
SG2-24
[10 empty] | 4.84 | 0.84 | 8
[10 empty] | 4 | 3.16 | 7.16
SG2-25
[10 empty] | 4.84 | 0.84 | 8
[10 empty] | 4 | 3.16 | 7.16
SG2-23
[10 empty] | 4.84 | 0.84 | 8
Activity |  |  |  |  | Predecessor | Time Estimates |  |  | Expected Duration
[6 empty] | Optimistic | Most Likely | Pessimistic
SG2-2:Create user Organizer |  |  |  |  | _ | 1 | 2 | 3 | 2
SG2-4:Create user Speaker |  |  |  |  | SG2-2 | 1 | 2 | 3 | 2
SG2-5:Create user Attendee |  |  |  |  | SG2-2 | 1 | 2 | 3 | 2
SG2-13:Send Invitation to Sponser |  |  |  |  | SG2-2 | 2 | 2 | 2 | 2
SG2-6:Able to track Speakers |  |  |  |  | SG2-4 | 1 | 2 | 3 | 2
SG2-3:Able to track Attendees |  |  |  |  | SG2-5 | 1 | 2 | 3 | 2
SG2-8:Able to delete Speaker |  |  |  |  | SG2-4 | 1 | 2 | 3 | 2
SG2-7:Able to delete Attendee |  |  |  |  | SG2-5 | 1 | 2 | 3 | 2
SG2-14:Show Attendees and Speakers |  |  |  |  | SG2-4,SG2-5 | 1 | 2 | 3 | 2
SG2-22:Graphical representation of Attendees |  |  |  |  | SG2-5 | 2 | 3 | 5 | 3.16
SG2-17:Graphical representation of speakers & Attendees |  |  |  |  | SG2-4,SG2-5 | 2 | 3 | 5 | 3.16
SG2-16:Send updates to Attendee |  |  |  |  | SG2-5 | 2 | 3 | 5 | 3.16
SG2-18:Upload presentaion materials |  |  |  |  | SG2-4 | 1 | 2 | 3 | 2
SG2-19:Update presentaion materials |  |  |  |  | SG2-4 | 1 | 2 | 3 | 2
SG2-9:Send updates to Speakers |  |  |  |  | SG2-4 | 2 | 3 | 5 | 3.16
SG2-15:Authorized presentation |  |  |  |  | SG2-18 | 1 | 2 | 3 | 2
SG2-20:Send session links |  |  |  |  | SG2-5 | 1 | 2 | 3 | 2
SG2-10:Speaker Q&A session |  |  |  |  | SG2-4,SG2-5 | 2 | 3 | 5 | 3.16
SG2-11:Attendee Q&A session |  |  |  |  | SG2-4,SG2-5 | 2 | 3 | 5 | 3.16
SG2-12: Attendee download presentation |  |  |  |  | SG2-4,SG2-5 | 1 | 2 | 3 | 2
SG2-24: Conduct,View polls |  |  |  |  | SG2-5 | 2 | 3 | 5 | 3.16
SG2-21:Able to generate reports |  |  |  |  | SG2-4,SG2-5 | 1 | 2 | 3 | 2
SG2-25:Implement payments |  |  |  |  | SG2-5 | 2 | 3 | 5 | 3.16
SG2-23:Digital certificates for attendees |  |  |  |  | SG2-5 | 2 | 3 | 5 | 3.16